## Calculations
Rules Used in Resource Calculations | [7 empty] | You change: | duration | add/sub units | work | chg % units
| Initial Assignment Calculation | Subsequent
Task Type |  | Constant | Input Variables | Calculated | Revision Strategy | Example | Comment | Task Type | Project will recalculate:
fixed-unit, effort-driven | work=duration x units | units |  |  | add resources to decrease duration | A piece of equipment will complete a job in 8 hours. Assign a second piece of equipment to halve the time. Doubling the work should double the duration. |  | fixed-unit, effort-driven | work | duration | duration | duration
|  |  | duration | work
|  |  | add/sub units | duration
|  |  | work | duration
|  |  | chg % units | duration
fixed-unit. | work=duration x units | units |  |  | add resources to decrease duration | Assign 2 gardners to work in garden for 3 days. Adding more gardners will get more work done, not change the duration. | If you redefine the assignment to "trim the beds", it becomes a different kind of task. | fixed-unit. | work | work | duration | duration
|  |  | duration | work
|  |  | add/sub units | work
|  |  | work | duration
|  |  | chg % units | duration
fixed-work, effort-driven | units=work / duration |  |  |  | add resources to complete sooner | A task requires 5 hours work to complete. Assign another resource to reduce the time, or have the resource work overtime. |  | fixed-work, effort-driven | units | duration | duration | no change
|  |  | duration | units
|  |  | units | duration
|  |  | work | duration
fixed-duration | work = units x duration |  |  |  | add/sub resources to predecessors | A 2 hour training class will take the same time if another instructor is added. |  | fixed-duration | work | work | units | work
|  |  | add/sub units | work
|  |  | chg % units | work
|  |  | work | units
|  |  | duration | work
fixed-duration, effort-driven | work = units x duration |  |  |  | adjust duration to decrease resources | A local farm will allow you all the fruit you can pick in an hour, but only one person can pick at a time. If you bring a friend, you have to take turns. |  | fixed-duration, effort-driven | units | units | units | work
|  |  | chg % units | work
|  |  | add/sub units | units
|  |  | duration | units
|  |  | work | units
Note: Examples are drawn from Mastering Microsoft Project 2000,by Gini Courter & Annette Marquis, 2000, available from Amazon.com.

## Lesson 4
Session 4
Project 2000, Lessons 2, 3
Lesson 2 | Evaluating & adjusting time factors
Lesson 3 | Evaluating & adjusting resources
Review
Open ResourceTrial project

## Task Relationships
Linking Relationships Defined
Type | Example | Comment
FS - Finish to Start | Distributing office furniture within the office cannot start until the furniture is received from the vendor. | This assumes that all the office furniture is received in a single delivery. The situation would be different if "Receive delivery" were a task involving multiple deliveries over some time period.
SS - Start to Start | When establishing a new office, tasks might include, "Receive resumes" and "Interview Candidates". Candidates cannot be interviewed prior to receiving their resumes, but interviews could begin before all resumes are received. | Lead time may be added to the "Interview .." task to allow time to set up interviews with the candidates whose resumes were received early in the process.
FF - Finish to Finish | The task, "Interview Candidates" might be divided into two tasks addressing "Sales Staff" and "Support Staff". In this event, "Support Staff" would not likely be completed until after "Sales Staff: is complete. | Interviewing "Support …" is the dependent, or Successor, task in this situation.
SF - Start to Finish | "Paint the Office" might be preceded by a task, "Mix and Deliver Paint". In this event, the Project Manager would not want the paint delivered too far in advance of the beginning of painting. | In this situation, the "Paint …" task is considered the predecessor to the "Mix …" task, even though it occurs after it.
Note: Examples are drawn from Mastering Microsoft Project 2000,by Gini Courter & Annette Marquis, 2000, available from Amazon.com.